## Sheet1
Sub-sys | Board | Schematic Complete | Layout Complete | Status
TPC Cold | HV | Done | Done | Quote Received, prototype not tested
| +/- 5V Telemetry Board | Done | Done | Quote Received, prototype not tested
| Light SiPM Preamp | Done | Done | Quote Received, prototype not tested
| Charge Preamp (5/ -5V) | Done | Done | Quote Received, prototype not tested
| +5V Telemetry Board | Done | Done | Prototype Tested, need to order final board
| SiPM Bias | Done | Done | Prototype Tested, need to order final board
TPC Warm | CAEN/Nevis DAQ (+/- 5V) | Done | Done | Requested Quote, prototype not tested
| CAEN/Nevis DAQ (+3.3V) | Done | Done | Quote not requested yet
| CAEN/Nevis DAQ (+12V) | Done | Done | Requested Quote, prototype not tested
| Shaper | Done | Done | Quote Received, prototype not tested
Flight Computer | Hub Computer | Not Started | Not Started | Quote not requested yet
| DAQ Computer | Not Started | Not Started | Quote not requested yet
TOF | TOF | Done | Done | Quote not requested yet
| MPD | Done | Done | Quote not requested yet
| TOF Bias | Done | Done | Quote not requested yet